## 2011-2012
Priority Action Group 5 - HIV Services
Work Plan 2013 - 2014
Task | Active work streams
| Work stream | Description/Details | Lead(s) - main leads are in bold | Related work stream | Timescale |  | Progress report November 2010
1 | BHIVA Testing Guidelines 2008 | Take forward implementation of BHIVA testing guidelines across Greater Manchester, identifying need for further guidance, training and data monitoring. | Ashley Pennell to speak to Andrew Turner re leading | Point of Care Testing (POCT) | December | 2009
2 | Policy - Point of Care Testing (POCT) | Develop Point of Care Testing guidelines for Greater Manchester | Andrew Turner, Sharon Wilson, Margaret Kingston, Diane Cordwell | BHIVA testing guidelines | April | 2011
5 | Primary Care - audit | To audit the number of patients continuing to access PC medication through outpatient clinics and monitor the shift in registrations with GP practices. Need to measure qualitative information e.g. confidentiality. Review patients' view of the change. Gather data about patient registration | Ash Sukthankar, HIV specialist pharmacists, Eleanor Roaf, Lynda Shentall, Sarah Stephenson | HIV database | Summer | 2010 | Ongoing. Problems with capacity and extracting relevant data.
7 | Shadowing of the tariff | Part of HIV Tariff project | Sarah Stephenson | Pathway mapping exercise | April | 2011 | Meeting arranged to progress November 2010
10 | HIV+ babies/children | Referral process, testing – GHT and Specialist Midwifery Service are looking at developing more joined up working around the re-offering of testing, health visitors | Sharon Wilson, Toni Tan, Lynda Shentall, Andrea Hughes (NWSCT) | Primary care, HIV strategy | Ongoing
12 | Social care framework | First social care framework for people living with HIV is being published | Lynda Shentall (GHT), Chris Morley (GHT), Simone Donohue (MCC) | HIV strategy | Ongoing
13 | Dental Care | During consultation several patients complained of poor access or poor experience with dental services across Greater Manchester. Manchester PCT's PALS and PPI colleagues will lead on future actions - PAG5 to review | Lynda Shentall requested re-opening this work stream. Sarah Stephenson - transferred to dental colleagues in Manchester PCT (no update as of Feb 2010). |  | Ongoing
15 | HIV Strategy | To agree a 10 year strategy for HIV care across GM. | PAG 6, Sarah Stephenson | Dental, Newfill, sperm washing, HIV babies/children, primary care, tariff shadowing, | September | 2010 | Ongoing as part of White Paper work
16 | Database of HIV+ patients | Database of HIV care across GM including drug regimes and other patient data to provide a more interactive and useful tool for recording and extracting information about HIV care. The quality and layout of informaiton in the haemophilia database would be the basis of this work. | Ash Sukthankar | Primary care, HIV strategy | Ongoing |  | Funding not secured. Ongoing as part of White Paper work
17 | Additional funding sources | For innovations, pilots, awards. All members of PAG 5 to be responsible for constant horizon scanning of funding or other opportunities | All |  | Ongoing
19 | Policy - Transitional Care Arrangements for children with HIV | This is a policy to manage care arrangements for adolescents moving from having their care managed by children's HIV services to adult services. This work will be led by the NWSCT but the policy will be shared with the Network before approval. | Toni Tan, Andrea Hughes (NWSCT), Sarah Stephenson, Lynda Shentall (also Julia from Barnardos), PAG 5. |  | Draft document circulated for comments
21 | Policy - Testing | Development of a policy for HIV testing in primary and secondary care and the community and voluntary sector (could follow similar pilot as carreid out by Leicester Medical Assessment Units) | PAG 5 (and Andrea Hughes if paeds involved) | HIV strategy | Ongoing
22 | Older people with HIV | To raise awareness of the ageing HIV population with the expectation that health and social care services will plan future services with this in mind | Bridget Hughes, Lynda Shentall, Pete Smith | HIV strategy, staff training | Ongoing
24 | Engagement with the public | Patient feedback mechanism in sexual health clinics | PAG 10 (A&C) | HIV strategy | Ongoing |  | System set up. Being piloted in Oldham and Bury first.
25 | Late Diagnosis | Late diagnosis of HIV (tie in with primary care education work done with PCTs last year and link in with feedback from Robert Darbyshire practice pilot and MRI work to test all medical admissions - this might be a more practical approach) | Ash Sukthankar, Eleanor Roaf? | Links to work stream 21 (Policy - Testing) | Ongoing
26 | Pharmacists' audit of HIV drugs | Savings, best practice | Ash Sukthankar, Sarah Stephenson | Primary care prescribing audit | Ongoing
27 | National BHIVA guidelines - refresh | Review national guidelines when they come out to see if there's value in adapting them for local use | Ash Sukthankar, Katherine Adjukiewicz |  | Ongoing
28 | Dry Blood Spot (DBS) Screening Project | Project to include DBS testing as part of the RU Clear programme | Diane Cordwell |  | Ongoing
29 | Policy - breastfeeding | To add a section to the maternity and neonatal policy to include a breastfeeding section (further to CHIVA's updated guidelines) | Sharon Wilson, Margaret Kingston, Val Finigan, Sarah Stephenson, Eleanor Roaf (via Sarah Stephenson) | Links to the maternity and neonatal policy | Completed
30 | Safeguarding evidence template re parental non-compliance for paediatrics on PEP | Template of information to present in court for the judge in relation to women who do not comply and babies at risk from not receiving PEP | Sharon Wilson, Margaret Kingston, Paddy McMaster, Eleanor Roaf (via Sarah Stephenson) | To be completed after work stream 29 is finished | Ongoing
31 | STI care pathway in TOP services | STI care pathway to be developed by PAG2 for use in all TOP services. To be reviewed by PAG5 before dissemination | Sarah Stephenson, Ash Sukthankar |  | Ongoing
32 | Specialist Midwifery Role | Forward planning for this role | Eleanor Roaf, Sarah Stephenson |  | Ongoing
Work streams on hold
18 | Policy - Dental Care | The progress of this work will depend on the outcome of the dental work being carried out by NHS Manchester. In the meantime, GHT are exploring the possibility of a 'you and your dentist' leaflet for patients. | Sarah Stephenson (liaison with Mark Carroll and Jules Palfreyman from NHS Manchester). Links to task 13 being managed by dental colleagues. | HIV strategy | Dependant on dental care work
6 | Primary Care - LES | Development of services in primary care - need to reference to HIV Strategy. This work is on hold until funding has been confirmed by NHS Manchester | Eleanor Roaf, Sarah Stephenson | HIV Tariff project
11 | Policy - Newfill | Cheshire and Merseyside are looking at developing their service to ensure it is properly funded. A protocol would ensure a uniform approach to providing dermal fillers. Due to PCT financial deficits, this work is on hold and will be reviewed in November 2009. | Sarah Stephenson, Emile Morgan (with Simon Henning from Cheshire and Merseyside and David Gibbins (Cumbria and Lancs) | HIV strategy
14 | Asylum | Prior to consultation clinicians reported problems in ensuring ongoing treatment for HIV where they were dispersed at short notice by the Home Office. | Sarah Stepenson | Primary care
8 | Pathway mapping exercise | Part of HIV Tariff project (to see if there are any blockages in the patient pathway and if there are, to find solutions) | Sarah Stephenson | Shadowing the tariff
Completed work streams
3 | Primary Care - education, confidentiality | To provide a training package on HIV for primary care staff for use by any PCT in Greater Manchester | Eleanor Roaf | All primary care work streams, HIV strategy | Completed
4 | Primary care - statutory training in PCTs | To improve awareness and index of suspicion of HIV amongst GM GPs. This training will be provided by SH commissioners as part of core PCT training days. Training pack to be copied to colleagues leading on dental training. | Eleanor Roaf, Andrew Mulholland, Lynda Shentall, Sharon Wilson | Primary care audit | Completed
20 | Policy - PEPSE | Policy for the assessment and prescribing of PEPSE across Greater Manchester | Ed Wilkins, Sarah Stephenson | HIV Strategy | Completed |  | Review in May 2012
23 | Policy - HIV+ professionals | GMC guidance available - just needs referencing so that we have a policy on record | Ash Sukthankar (link to NAT work), Sarah Stephenson | HIV strategy | Completed
9 | Policy - sperm washing (fertility guidance for HIV discordant couples) | Agree protocol and process for infertility processes for HIV discordant couples. Currently patietns have to travel to London for treatment and a local protocol would be more convenient for patients and more cose-effective for commissioners (funding discussions through commissioning leads) | Orla McQuillan, Chitra Babu, Sarah Stephenson, Sarah Doran, Eleanor Roaf, Sharon Wilson | HIV strategy | Completed |  | Review in January 2014